## Sheet1
Date | Team Members | Goals | Task Completed | Time Duration
2016-02-24 | Htoo, Shannon | Learn Github, gnuradio software, Hamming code, set team roles, set Milestones | Set up Github accounts, researched Hamming code (decided on (8,4)), set team roles, set Milestones and began understanding gnuradio software | 4:30 - 5:30pm
2016-02-27 | Htoo | Began writing Hamming code | Finished planning and basic outline/procedure to follow when writing the Hamming code | 4:00-5:00 pm
2016-02-28 | Shannon | Learn Github | Completed tutorial of Github | 7:00-9:00pm
2016-03-03 | Htoo, Shannon | Create encoder - flowchart, start coding hamming code | Finished encoder flowchart, began decoder flow chart, began hamming code | 8:00-10:00pm
2016-03-05 | Shannon | decoder flow chart | research methods for creating decoder flow chart | 4:00-5:00 pm
2016-03-06 | Htoo | hamming code power point | completed power point | 10:00-11:00 pm
Spring Break | Htoo | complete draft of hamming code | found out that in order to make a flow chart block for the hamming code, the code must be in C++ | 3 hrs
Spring Break | Shannon | decoder research | continued reseach | 3 hrs
2016-03-23 | Htoo, Shannon | finish decoder flow chart, start to write hamming code in C++ | Finished decoder flow chart, began to debug | 5:00-6:00pm
2016-03-25 | Htoo, Shannon | have the flowchart fully functioning, begin to write hamming code in C++ | Worked on debugging the flowchart | 2:00-3:00pm
2016-03-30 | Htoo, Shannon | Write GNU block descriptions for encoder and decoder | Wrote descriptions for encoder blocks and worked on debugging the flowchart | 11:30am-1:00pm
2016-04-06 | Htoo, Shannon | debug flowchart | First corrected the encoder block descriptions, then continued debuggin the flowchart | 11:30am-1:00pm
2016-04-06 | Htoo, Shannon | complete poster | Worked as a team on the poster, completed poster (note: needs to be turned in Fri before 6pm) | 4:30-5:30pm
2016-04-13 | Htoo, Shannon | debug flowchart, work on gnu block descriptions | Added a few more decriptions to the gnu block descriptions, worked on debugging flowchart | 11:00am-1:00pm
2016-04-20 | Htoo, Shannon | debug flowchart | changed flowchart - placement of integration boxes. Still is not working properly | 11:00am-1:00pm
2016-04-26 | Htoo, Shannon | work on organizing documenation | Edited meeting summaries | 1 hr
2016-04-27 | Htoo, Shannon | complete documentation, work on gnu block description, debugging flow chart | completed documentation, continued to work on block descriptions, tried to debug flow chart | 11:00am-1:00pm
2016-04-28 | Htoo, Shannon | work on gnu block descriptions | gnu block descriptions | 2 hrs
Note:
Group meetings have been moved to Wednesdays at 1:00 pm
Activity Log